EDINBANE COMMUNITY COMPANY

MEETING MINUTES

THURSDAY 27TH MAY 2021

Present- joe kalaher,Alistair danter, roddy MacFarlane,ian Brown,Andrew prendagast,phil ashurst,stuart whatley.

Apologies- Davina macluskie,billy shanks.

Previous minutes- Approved.

Proposed -AD

Seconded-SW

Action points-previous minute

Land fund to be thanked-completed IB

Shop survey- completed ( agreed to pay 50% for 6 months)

Complaint procedure- RM to approach slcvo.

Letter of concern to roads-completed IB

Painting shop- agreed to go ahead.

Agreed Decisions

-SHOP PROJECT

-Agreed- Order large skip when reqd.

-Agreed- Pay 50% council tax for 6 mths.

-Agreed- Shop to be painted.

-SUSTRANS PATH

-Agreed-Correspondence could be public.

-VILLAGE SIGNAGE

-Agreed-Wait until further progress.

HARDSHIP FUND

-Agreed-ecc could hold hc funds if needed.

Development worker report

- AFFORDABLE HOUSING

- pp not yet granted

- Ap fully briefed on project

- Awaiting a grant approval in july.

- SUSTRANS PATH.

- Extra sustrans funds applied for to cover traffic survey/safety ass.

- Awaiting £27,700 sustrans grant.

- Path displays in place

- Little response from app.

- Road consent could be 40k not 4k

- Eco survey completed.

- Drawings due to be updated.

- RENOVATION PATH.

- Planning application submitted.

- No. of signs reduced.

- Gates removed from path plan.

- Grant from ccf accepted.

- Bat survey ongoing.

- Suggestion to use village maintenance for new path or approach council.

- SHOP PROJECT

- Funds needed for architect fees.

- AD requested project recap from AP at next meeting.

- VILLAGE CENTRE

- Awaiting report from M.Henry.

- JK to progress with village traffic and people nos.

New Development worker.

- Andrew Prendergast is authorized to deal with Ecc's lawyer,funding bodies and their agents, sll and their agents and to work to further Ecc projects.

- Agreed AP will work 10 days a month at £150 per day.

Financial.

- Payment of £2000 to IB outstanding.

- SW agreed to check sustrans grant had been received.

- School project cheque still to be paid.

Correspondence

- None.

Donm

- Thursday 24th June 2021.